NAME : VERONICA OPEYEMI AJAYI

COURSE: GRC 205  Incident Management and Business Continuity

REG NUMBER : GCR/2025/12815

Business Continuity and Disaster Recovery

Northbridge Skills Institute

1.Business Impact Analysis

Northbridge Skills Institute has 1,800 learners and 90 staff. At 08:00 WAT on Day 0, flooding and a power failure make the main site and local systems unavailable. Facilities estimates that the site will remain inaccessible for 72 hours. Microsoft 365 identity and email remain available through mobile internet. An alternate facility is available from 10:00 with 25 workstations.

The BIA identifies five important business functions.

| Function | Owner role | Users affected. | Critical resources | Dependencies | Key impact | Minimum acceptable service. | Priority |
| --- | --- | --- | --- | --- | --- | --- | --- |
| F1 Teaching & Assessment | Academic/Assessment Manager | 120 examination learners, teaching staff | LMS01, DB01, exam records, workstations | Network, AUTH01, DB01, LMS01, staff, alternate facility | Examination starts 11:00; failure causes NGN120,000 rescheduling cost plus learner/reputation impact | Secure examination service for all learners, with approved alternative arrangements for learners without centre workstations | 1 |
| F2 Fees & Finance | Finance Manager | Finance staff, learners, payment provider. | FIN01, DB01, payment records | Network, AUTH01, DB01, payment provider, finance staff | Admissions closes 18:00; applications and registration changes cannot be entered | Receive/confirm payments, preserve transaction evidence and reconcile later | 2 |
| F3 Admissions & Registration | Admissions Manager. | Applicants and registration staff | REG01, DB01 | Network, AUTH01, DB01, staff | Admissions closes 18:00; applications and registration changes cannot be entered | Capture applications and registration changes through controlled temporary records | 3 |
| F4 Staff Payroll | HR/Payroll Manager | 90 staff and payroll staff | HR01, DB01 | Network, AUTH01, DB01, bank, payroll staff. | Bank submission deadline is 12:00 Day 1; duplicate/incorrect instructions create financial and staff impact | Prepare and verify payroll instructions using controlled records before submission | 4 |
| F5 Records & Certificates | Records Manager | Learners requesting records/certificates | FS01 | Network, AUTH01, FS01, authorised staff | 48-hour internal service commitment may be missed | Access protected records and process urgent requests within the 48-hour commitment | 5 |

Impact Calculations

The assignment instructs that the hourly costs are separate and non-overlapping and should be applied for the first 24 hours. The examination rescheduling cost of NGN120,000 is added once when its trigger is reached.

8-hour disruption

F1:
NGN60,000 × 8 = NGN480,000
Exam rescheduling trigger = NGN120,000
F1 total = NGN600,000

F2:
NGN40,000 × 8 = NGN320,000

F3:
NGN20,000 × 8 = NGN160,000

F4:
NGN10,000 × 8 = NGN80,000

F5:
NGN5,000 × 8 = NGN40,000

Combined 8-hour impact:

NGN600,000 + NGN320,000 + NGN160,000 + NGN80,000 + NGN40,000
= NGN1,200,000

24-hour disruption

F1:
NGN60,000 × 24 = NGN1,440,000

NGN120,000 examination rescheduling cost
= NGN1,560,000

F2:
NGN40,000 × 24 = NGN960,000

F3:
NGN20,000 × 24 = NGN480,000

F4:
NGN10,000 × 24 = NGN240,000

F5:
NGN5,000 × 24 = NGN120,000

Combined 24-hour impact:

NGN1,560,000 + NGN960,000 + NGN480,000 + NGN240,000 + NGN120,000
= NGN3,360,000

Limitations of the Estimates

First, the hourly figures do not capture indirect consequences such as loss of learner confidence, reputational damage, staff overtime, regulatory consequences or supplier penalties.

Second, the model assumes that disruption costs increase linearly each hour. Actual losses may increase disproportionately when important deadlines are missed.

Financial impact is therefore only one part of the BIA. Learner welfare, assessment integrity, confidentiality, availability of records, institutional reputation and the ability to meet contractual or regulatory obligations are also important.

Business Priority versus Technical Recovery Order

The business priority is:

F1 → F2 → F3 → F4 → F5

However, the technical restoration sequence cannot simply follow this order because F1–F4 share DB01, while all functions depend on the recovery network and authentication infrastructure.

The technical sequence is:

Recovery Network → AUTH01 → Security/Backup Checks → DB01 → Applications

FS01 can begin after AUTH01 and security/backup checks and can run in parallel with DB01 restoration.

The three major dependency risks are:

- DB01 dependency risk: F1–F4 cannot operate until DB01 is restored.

- AUTH01 dependency risk: Local authentication is required before local applications can be used.

- Backup/security dependency risk: Restoring data before validating backup integrity or investigating suspicious administrator activity could introduce corrupted or unauthorised data.

TASK 2

RECOVERY OBJECTIVES AND BACKUP DESIGN

| Function | RTO | RPO | MTD | Justification |
| --- | --- | --- | --- | --- |
| F1 Teaching & Assessment | 2 hours | 1 hour | 3 hours | 11:00 examination creates very little tolerance |
| F2 Fees & Finance | 4 hours | 1 hour | 8 hours | Fee confirmation due by 16:00 |
| F3 Admissions | 6 hours | 4 hours | 12 hours | Admissions closes at 18:00 |
| F4 Payroll | 12 hours | 4 hours | 24 hours | Bank deadline is 12:00 Day 1 |
| F5 Records & Certificates | 24 hours | 12 hours | 48 hours | 48-hour service commitment |

Recovery should be declared only when the technology is restored and the business owner confirms that minimum service works, leaving a buffer before MTD.

Calculations

| System | Latest checkpoint | Age at 08:00 | Assessment |
| --- | --- | --- | --- |
| DB01 | 07:00 Day 0 | 1 hour | Meets proposed 1-hour RPO if chain is valid |
| AUTH01 | 00:00 Day 0 | 8 hours | Recovery-point gap against the proposed 4-hour target |
| FS01 | 23:00 Day -1 | 9 hours | Meets proposed 12-hour RPO |

DB01 should use B01 followed by every required valid incremental through 07:00. Temporary payment, admissions, assessment and other records can support reconciliation after restoration, but the Institute must not assume that every post-checkpoint change is recoverable.

The backup design should include daily full backups, hourly DB01 incremental during operating periods, frequent AUTH01 snapshots, FS01 incremental, encryption, offsite storage, retention controls and at least one independent offline or immutable copy. Backup administration should use separate privileged accounts and MFA rather than the shared production administrator identity.

The DB01 restoration chain is: B01 full backup → required incremental through the selected recovery point → integrity validation → database recovery → application and business validation. Restoration tests should verify integrity, access independence, database consistency, application login and transaction processing. Offsite storage or a live replica alone does not prove recoverability.

TASK 3: RECOVERY STRATEGY AND BUDGET

| Package | Base | Backups | Training/tests | Annual total | Recovery | Data-loss |
| --- | --- | --- | --- | --- | --- | --- |
| Cold | NGN600,000 | NGN400,000 | NGN200,000 | NGN1,200,000 | 24–48 hrs | Up to 24 hrs |
| Warm | NGN1,500,000 | NGN400,000 | NGN200,000 | NGN2,100,000 | 3–5 hrs | 1–6 hrs |
| Hot | NGN2,400,000 | NGN400,000 | NGN200,000 | NGN3,000,000 | About 1 hr | Up to 15 mins |

All three options fit the NGN3,000,000 annual limit. Cold is too slow for the examination and Day 0 deadlines. Hot offers the strongest capability but consumes the entire budget. The recommended option is the Warm site because it balances capability and affordability at NGN2,100,000 annually, leaving NGN900,000 below the limit.

The main residual risk is that the estimated 3–5-hour recovery window cannot guarantee the F1 two-hour RTO. Management should formally accept this risk and rely on temporary assessment continuity arrangements. The 8-hour disruption estimate is NGN1,200,000 and the 24-hour estimate is NGN3,360,000, but one outage cannot establish annual ROI. Supplier recovery evidence, SLAs, restoration tests and actual RTO/RPO measurements should be reviewed before expenditure approval.

TASK 4: BUSINESS CONTINUITY AND DISASTER RECOVERY PLAN

The plan should be activated when the site is unavailable for more than 30 minutes, a critical service is likely to miss its RTO, the site is unsafe, or disruption is expected to exceed business tolerance. The Institute Director is the authorised decision maker and the Business Continuity Coordinator is the deputy. The continuity team manages services and communication; IT restores systems; Facilities confirms safety; Incident Response investigates suspected compromise.

| Activity | Accountable | Responsible | Consulted |
| --- | --- | --- | --- |
| Activate BCP/DR | Institute Director | BC Coordinator | Facilities, IT |
| Temporary assessment | Assessment Manager | Assessment Team | IT, Learner Support |
| Backup validation | IT/DR Lead | Technicians | Incident Response |
| System restoration | IT/DR Lead | Technicians | Application Owners |
| Stakeholder communication | BC Coordinator | Learner Support/Communications | Director |
| Return to primary site | Institute Director | Facilities and IT | BC Coordinator, Business Owners |

Temporary Procedures

F1: Use the 25 alternate workstations for the most critical centre-based assessment needs, arrange additional secure capacity where possible, and use personal devices for the 80 learners who can use them. Maintain identity checks, invigilation, accessibility, secure submissions and later reconciliation.

F2: Continue using the external payment provider and keep a controlled temporary transaction register with reference, amount, time and approval status. Reconcile it to FIN01 after restoration.

F3: Capture applications and registration changes using an approved temporary form or restricted spreadsheet and enter/check them after REG01 restoration.

F4: Prepare payroll from verified records and require a second authorised person to review totals, bank details and duplicate-payment risks before submission.

F5: Log urgent records/certificate requests manually, restrict access to authorised staff and reconcile with FS01 after restoration.

DR Runbook

1. Activate the plan. 2. Confirm site safety and alternate-site availability. 3. Establish the recovery network. 4. Restore AUTH01. 5. Complete security and backup checks. 6. Validate backup integrity. 7. Restore DB01 from B01 and valid incremental. 8. Restore FS01 after prerequisites. 9. Validate DB01. 10. Restore LMS01, FIN01, REG01 and HR01. 11. Test applications and authentication. 12. Obtain business acceptance. 13. Reconcile temporary records. 14. Declare services operational. 15. Monitor. 16. Return only after facilities clearance and controlled data transfer.

If a backup fails integrity validation, stop using that chain and select an earlier known-good or independent protected copy. If restored data is inconsistent, isolate the system, investigate and roll back rather than releasing unreliable data.

Stakeholder Communication

| Stakeholder | Information | Channel | Owner | Frequency |
| --- | --- | --- | --- | --- |
| Learners | Exam/service instructions | Microsoft 365/email/SMS | Learner Support | Activation and major updates |
| Staff | Work arrangements/recovery | Email/Teams/mobile | BC Coordinator | Every 2 hours |
| Management | Situation, risks, decisions | Situation report | BC Coordinator | Every 2 hours |
| Suppliers | Recovery requirements | Phone/email | IT/Procurement | As required |
| Facilities | Safety/access status | Phone/email | Facilities Lead | Major changes |

Initial Learner Notice

Learners are informed that today's on-site facilities are temporarily unavailable because of flooding and a power failure. Your safety remains our priority. The 11:00 examination will proceed using approved temporary arrangements where possible. Learners who can use their own devices should follow the instructions sent through Microsoft 365. Learners assigned to centre workstations will receive their allocated time, location and access instructions; the Institute is arranging additional capacity where required. Do not travel to the main campus until a formal reopening notice is issued. Please keep examination materials and submission evidence secure and do not share assessment content. If you experience access problems, contact Learner Support through the alternative channel provided. Further updates will be issued as the situation develops. We apologise for the disruption and appreciate your cooperation.

Possible compromise triggers Incident Response where there is evidence of unauthorised access, suspicious administrator activity, malware, compromised credentials, corrupted data or unexplained changes. Return requires facilities clearance, controlled transfer of outage records and final sign-off by management and business owners.

TASK 5: RECOVERY SCHEDULE AND EXERCISE

| Action | Technician | Start | Finish | Prerequisite |
| --- | --- | --- | --- | --- |
| Recovery network | T1 | 08:00 | 08:30 | None |
| AUTH01 restoration | T1 | 08:30 | 09:00 | Recovery network |
| Security and backup checks | T1 | 09:00 | 09:30 | AUTH01 |
| DB01 restoration | T1 | 09:30 | 11:00 | Security/backup checks |
| FS01 restoration | T2 | 09:30 | 10:30 | AUTH01 + security checks |
| LMS01 restoration | T1 | 11:00 | 11:45 | DB01 |
| HR01 restoration | T2 | 11:00 | 11:45 | DB01 |
| FIN01 restoration | T1 | 11:45 | 12:15 | DB01 |
| REG01 restoration | T2 | 11:45 | 12:15 | DB01 |

The assessment critical path is Recovery Network → AUTH01 → Security/Backup Checks → DB01 → LMS01. It takes 225 minutes, so LMS01 is restored at 11:45. This misses the 11:00 examination start by 45 minutes, requiring a continuity workaround.

| Function | Modelled recovery | RTO | MTD | Result |
| --- | --- | --- | --- | --- |
| F1 | 3h45m | 2h | 3h | Fails without workaround |
| F2 | 4h15m | 4h | 8h | Slight RTO miss; within MTD |
| F3 | 4h15m | 6h | 12h | Meets |
| F4 | 3h45m | 12h | 24h | Meets |
| F5 | 2h30m | 24h | 48h | Meets |

These are modelled baseline results, not live-test results. DB01 has a one-hour data-loss window, FS01 has a nine-hour window and AUTH01 has an eight-hour window. The AUTH01 result remains a recovery gap.

45-Minute Tabletop Exercise

| Time | Inject | Decision | Owner | Effect |
| --- | --- | --- | --- | --- |
| 10 min | Closure extends to five days | Continue alternate-site operations and extended continuity | BC Coordinator | Additional resources required |
| 20 min | Only 15 workstations available | Prioritise critical assessment users and obtain more capacity | Assessment Manager | Higher assessment risk |
| 30 min | DB01 incremental fails; unexpected backup admin logon | Reject backup, preserve evidence and involve Incident Response | IT/DR + IR | Use earlier known-good copy if necessary |
| 40 min | Payments missing from restored finance records | Reconcile against provider evidence using controlled exceptions | Finance Manager | Finance remains partially operational |

Corrective Actions

| Priority | Action | Owner | Target | Evidence |
| --- | --- | --- | --- | --- |
| Critical | Separate backup and production administrator identities | IT Manager | 30 days | Separate privileged accounts tested |
| Critical | Implement independent immutable backup | IT Manager | 45 days | Successful restore test |
| High | Improve AUTH01 backup frequency | IT Lead | 30 days | Four-hour snapshot evidence |
| High | Increase alternate-site workstation capacity | BC Coordinator | 60 days | 40 secure workstations available |
| High | Test payment reconciliation with provider | Finance Manager | 45 days | Completed reconciliation exercise |

TASK 6: GOVERNANCE AND PERFORMANCE MEASURES

The Business Continuity Coordinator owns the BCP/DR plan. The Institute Director approves it and accepts significant residual risks. The IT/DR Lead owns technical recovery procedures. The plan should be reviewed annually, after incidents, major technology or supplier changes, failed exercises and significant dependency changes.

| Frequency | Test/review |
| --- | --- |
| Monthly | Backup integrity checks |
| Quarterly | Critical application restoration tests |
| Every 6 months | Tabletop exercise |
| Annually | Full BCP/DR exercise |
| After major change | Targeted recovery test |
| After major incident | Lessons-learned review |

NIST SP 800-34 Mapping

| Assignment output | NIST planning step |
| --- | --- |
| BIA | Conduct business impact analysis |
| Recovery strategy | Identify preventive controls/recovery strategies |
| DR runbook | Develop IT contingency plan |
| Tabletop/recovery tests | Plan testing, training and exercises |
| Annual review | Plan maintenance |

NIST SP 800-34 Rev. 1 describes contingency planning as a structured process that includes assessing requirements and priorities, developing recovery strategies, contingency plans, testing/training/exercises and plan maintenance.

ISO 22301 Alignment

| Output | ISO 22301 theme |
| --- | --- |
| BIA | Context and requirements |
| Management approval | Leadership |
| RTO/RPO/MTD and strategy | Planning |
| Training and communications | Support |
| Temporary procedures/runbook | Operation |
| KPIs/tests/review | Performance evaluation |
| Corrective actions | Improvement |

ISO 22301:2019 provides a framework for planning, establishing, implementing, operating, monitoring, reviewing, maintaining and continually improving a business continuity management system. The 2024 climate-action amendment supports consideration of climate-related issues.

Flood risk should be included in the continuity risk assessment because flooding can affect premises, power, local systems and physical access. Controls should include flood-risk assessment, equipment protection, backup power, alternate-site planning, evacuation arrangements and supplier continuity.

Performance Dashboard

| KPI | Measurement | Target | Frequency | Owner |
| --- | --- | --- | --- | --- |
| RTO achievement | Critical recoveries within RTO ÷ total tested ×100 | ≥95% | Quarterly | IT/DR Lead |
| Restoration-test coverage | Critical systems tested ÷ critical systems ×100 | 100% annually | Quarterly | IT Manager |
| Corrective-action closure | Actions closed by due date ÷ actions due ×100 | ≥90% | Monthly | BC Coordinator |
| Training completion | Staff trained ÷ required staff ×100 | ≥95% | Quarterly | HR/BC Coordinator |
| Backup success | Successful jobs ÷ scheduled jobs ×100 | ≥98% | Monthly | IT Lead |
| Exercise success | Objectives achieved ÷ objectives tested ×100 | ≥90% | Six-monthly | BC Coordinator |

Maturity Assessment and 12-Month Target

Based on the scenario, Northbridge is at a Developing level because it has backups, an alternate facility and recovery procedures, but weaknesses remain in backup administration, recovery-point capability, alternate-site capacity, supplier evidence and tested assumptions.

The 12-month target is to reach the next maturity stage by implementing independent privileged backup access, immutable/offline backups, quarterly restoration tests, an annual full recovery exercise, documented supplier recovery evidence, adequate alternate-site capacity, at least 95% training completion, at least 95% critical RTO achievement and at least 90% corrective-action closure by due date.

The Northbridge scenario demonstrates that continuity cannot depend solely on technology restoration. F1 Teaching and Assessment is the highest business priority because of the 11:00 deadline, but the technical dependency chain means LMS01 cannot be restored until the recovery network, AUTH01, security/backup checks and DB01 are completed. The modelled baseline restores LMS01 at 11:45, so a temporary examination arrangement is essential.

The warm-site strategy is recommended at NGN2.1 million annually because it balances resilience and affordability, although management must accept the residual risk associated with its 3–5-hour recovery estimate. The backup programme should strengthen independent access, immutable/offline copies, encryption, integrity checking and restoration testing. Continuous testing, KPIs and corrective actions should improve BCDR maturity over the next 12 months.

REFERENCES

International Cybersecurity and Digital Forensics Academy (ICDFA). (2026). Business Continuity and Disaster Recovery: GRC205 Incident Management and Business Continuity, Week 21 Teaching Materials.

International Organization for Standardization (ISO). (2019). ISO 22301:2019: Security and resilience — Business continuity management systems — Requirements. ISO.

International Organization for Standardization (ISO). (2024). ISO 22301:2019/Amd 1:2024: Climate action changes. ISO.

Swanson, M. M., Bowen, P., Phillips, A. W., Gallup, D., & Lynes, D. (2010). Contingency Planning Guide for Federal Information Systems (NIST Special Publication 800-34 Revision 1). National Institute of Standards and Technology.

AI ASSISTANCE ACKNOWLEDGEMENT

AI assistance was used to support the organisation, drafting  of this assignment. The student remains responsible for reviewing the content, calculations, assumptions and final submission.